## P0-7_LIVE_PILOT_README
ECRI P0-7 Live Multi-Assessor Pilot | v1
Purpose | Empirically test assessor reliability, evidence-coding reliability, construct interpretation, scoring stability, burden, routing behaviour, and preliminary validity before ECRI methodology freeze.
Basis | ECRI v1.3 calibrated/repaired master engine: exactly 11 dimensions, 132 canonical metrics, calibrated maturity decision tests, contradiction hierarchy, N/A tests and high-stakes controls.
Status | PILOT-READY PROTOCOL — NO EMPIRICAL RESULTS YET
Minimum pilot | 8–12 institutions; 3 assessors; 4–6 full assessments; ≥20% retest subset where feasible; 10–20 cognitive interviews.
Preferred pilot | 15–25 institutions; 5–8 assessors; broader institutional/context coverage and multiple independent assessment pairs.
Critical rule | Pilot data may change anchors, thresholds, weights, routing and evidence rules. Do not freeze those parameters merely because the synthetic rounds passed.
Unit of analysis | Institution-level ECRI assessment, with programme/learner/employer/outcome evidence as applicable.
Independence | Assessors must score independently before adjudication. Adjudicated values are retained separately from raw assessor values.
Synthetic vs live | Round 5 was synthetic calibration. This workbook is the operational protocol for the next live phase; no live pilot has been conducted by this file.

## 01_Pilot_Design
Field | Protocol | Acceptance / Decision Rule
Pilot type | Prospective multi-assessor methodology pilot | Real institutional cases; evidence-based scoring
Minimum institutions | 8–12 | Below 8 = exploratory only
Preferred institutions | 15–25 | Preferred for stable subgroup and reliability estimates
Assessors minimum | 3 | Preferred 5–8
Independent duplicate assessments | ≥4–6 full assessments | Each duplicate institution scored independently by ≥2 assessors
Retest subset | ≥20% where feasible | Same evidence/time-bounded repeat scoring; assess stability
Cognitive interviews | 10–20 | Test comprehension and response-process validity
Burden logging | All assessments | Capture respondent time, assessor time, evidence volume, routing burden
Pilot freeze | Version-controlled build | No methodology changes mid-case; changes require new build/version
Primary outputs | Reliability + validity + calibration + burden + fairness | Feed P0-7 calibration decision and P0-5/P0-4 revisions

## 02_Institution_Sampling
Stratum | Target Count | Examples / Inclusion Logic | Why Included | Minimum Evidence Condition
General university | 2–4 | Comprehensive multidisciplinary university | Baseline construct coverage | Graduating cohort preferred
Employment-intensive / professional | 2–4 | Engineering, management, health, professional institutions | Tests employer/placement intensity | Outcome data preferred
Research-intensive | 1–3 | Research-led university | Tests contextual required-maturity rules | Do not penalize legitimate outcome structure
Specialised institution | 1–3 | Specialized professional/technical/art/design institution | Tests N/A and construct relevance | Construct-specific applicability required
New/emerging institution | 1–2 | Limited graduating cohorts | Tests legitimate outcome N/A handling | Document cohort age and outcome availability
Strategic-priority institution | 1–3 | Institution with explicit employability priority | Tests required-maturity logic | Strategy evidence + operating evidence

## 03_Recruitment_Data_Governance
Control | Requirement | Record
Institution invitation | Participation is voluntary and methodology-focused | Institution ID
Confidentiality | Report pilot findings in aggregate unless explicit permission exists | Disclosure status
Data minimisation | Collect only evidence needed for assessment/validation | Data owner
Evidence provenance | Every material claim must have source/date/owner | Evidence ID
Assessor confidentiality | Individual assessor results are used for reliability analysis, not public ranking | Assessor ID
Conflict declaration | Assessor declares conflicts before assignment | Conflict status
Version control | Record master engine version, protocol version and calibration layer version | Version IDs
Data retention | Set retention/deletion rule before live data collection | Retention decision

## 04_Assessor_Roster
Assessor ID | Role / Expertise | Years Relevant Experience | Conflict of Interest | Calibration Completed | Calibration Score / Notes | Assigned Cases

## 05_Case_Register
Case ID | Institution ID | Context | Cohort Availability | Primary Assessor | Secondary Assessor | Retest? | Assessment Version | Status | Adjudication Required

## 06_Assessment_Control
Case ID | Stage | Start Date | End Date | Respondent Hours | Assessor Hours | Evidence Items | Metrics Applicable | Metrics N/A | High-Stakes Flags | Contradictions | Routing Overrides | Burden Rating | Notes

## 07_Evidence_Log
Case ID | Evidence ID | Metric ID | Evidence Type | Source Role | Date | E0-E4 Code | Authenticity Checked | Independent Corroboration | Outcome Linkage | Reused Elsewhere? | Reuse Allowed? | Assessor Notes

## 08_Assessor_Scoring
Case ID | Assessor ID | Metric ID | Applicable? | Maturity 0-5 | Implementation 0-5 | Outcome 0-100 / N/A | Evidence E0-E4 | Maturity Decision Test Passed? | N/A Gate Passed? | High-Stakes Verified? | Contradiction Flag | Assessor Confidence | Comments

## 09_Adjudication
Case ID | Metric ID | Assessor A | Assessor B | Initial Spread | Construct Boundary Check | Evidence Hierarchy Applied | N/A Test Applied | High-Stakes Rule Applied | Adjudicated Maturity | Adjudicated Implementation | Adjudicated Outcome | Adjudicated Evidence | Reason Code | Release Hold? | Adjudicator Notes

## 10_Reliability_Analysis
Analysis | Unit | Minimum Calculation | Interpretation / Flag | Observed Result | Decision
Exact agreement | Metric/case | % exact maturity agreement | Descriptive; inspect borderline levels
Adjacent agreement | Metric/case | % within ±1 maturity level | Primary calibration indicator
Max spread | Metric/case | max assessor difference | Investigate >1 routinely; adjudicate >1
Weighted kappa | Maturity ratings | Quadratic weighted kappa where sample permits | Report CI where feasible
ICC | Continuous/near-continuous scores | ICC appropriate to design | Use assessor model consistent with study design
Evidence coding agreement | Metric/case | Agreement on E0–E4 | Review disagreements in evidence interpretation
N/A agreement | Metric/case | % same N/A decision | Low agreement indicates construct/applicability ambiguity
Adjudication rate | Metric/case | % metrics requiring adjudication | High rate indicates anchor weakness
Retest stability | Institution/metric | ICC/kappa or score correlation as appropriate | Investigate material drift
Burden | Assessment | hours / evidence items / questions | Balance validity with operational feasibility

## 11_Validity_Analysis
Validity Evidence | Data Source | Method | What Would Support ECRI | What Would Trigger Repair
Content validity | Expert review | Structured CVI/qualitative review | Metrics cover intended construct without major omissions | Construct gaps or excessive redundancy
Response-process validity | Cognitive interviews | Think-aloud + probing | Respondents interpret questions as intended | Systematic misunderstanding
Construct validity | Metric scores + qualitative evidence | Known-groups / dimensional analyses as appropriate | Expected pattern without contamination | Unexpected cross-construct collapse
Criterion validity | External outcome records | Association with relevant employment/career outcomes | Meaningful association where theoretically expected | Weak/contradictory relationships
Convergent validity | Related employability measures | Correlation / pattern comparison | Moderate expected convergence | Near-zero or implausibly high convergence
Discriminant validity | Distinct institutional constructs | Correlation / HTMT or analogous analysis where suitable | Related but separable constructs | Metrics appear redundant
Predictive validity | Longitudinal outcomes where feasible | Prospective association | Early capability signals predict later outcomes | No useful predictive signal after adequate sample
Fairness / invariance | Institutional subgroup data | Differential functioning / subgroup comparison | No unjustified systematic penalty | Context-driven bias requiring redesign

## 12_Pilot_Hypotheses
ID | Hypothesis | Expected Pattern | Test | Repair if Fails
H01 | Maturity anchors improve inter-rater consistency | Higher exact/adjacent agreement than Round 4 synthetic baseline | Compare duplicate cases and metric-family agreement | Revise affected family exemplars/decision tests
H02 | Evidence confidence is separable from performance | Evidence level does not mechanically determine score | Correlation / distribution review | Check evidence-performance leakage
H03 | Outcome metrics capture outcomes without back-casting capability | Outcome and maturity/implementation can diverge | Case-level diagnostic review | Strengthen outcome/capability boundary
H04 | N/A is construct-driven | N/A decisions are consistent and evidence-based | N/A agreement + adjudication review | Add construct-specific N/A examples
H05 | Routing reduces burden without changing score rules | Fewer questions/evidence requests with no scoring bias | Burden and route audit | Revise routing triggers/stop rules
H06 | Anti-gaming controls resist headline claims | Volume claims do not create high scores without quality evidence | Adversarial claim review inside live cases | Add verification rules
H07 | D11 behaves as a meta-capability | Continuous improvement intelligence is distinguishable from generic governance | Construct review / qualitative analysis | Refine boundaries if contaminated

## 13_Calibration_Session
Session | Activity | Required | Pass Criterion | Record
C01 | Independent exemplar scoring | All assessors | No discussion before first rating | Ratings captured
C02 | Group rationale comparison | All assessors | Differences linked to explicit evidence/rule | Decision notes
C03 | Borderline 2/3 cases | All assessors | Correct distinction: isolated pilot vs repeatable structured mechanism | Agreement / repairs
C04 | Borderline 3/4 cases | All assessors | Integration requires workflow linkage + decision use + ownership + QA | Agreement / repairs
C05 | Borderline 4/5 cases | All assessors | Adaptation requires demonstrated learning cycles, not activity volume | Agreement / repairs
C06 | Contradiction case | All assessors | Hierarchy applied; unresolved contradiction holds release | Agreement / repairs
C07 | N/A case | All assessors | Construct-specific N/A test passed | Agreement / repairs
C08 | High-stakes case | All assessors | Enhanced verification required | Agreement / repairs

## 14_Pilot_Decision_Rules
Gate | Preferred / Target | Minimum | Fail / Repair Trigger
Exact agreement | ≥80% on duplicate ratings | ≥70% | <70%: mandatory anchor review
Adjacent agreement | ≥95% | ≥90% | <90%: family-level calibration repair
Max spread | ≤1 routinely | ≤2 | >2 on material metrics: adjudication + anchor repair
N/A agreement | ≥90% | ≥80% | <80%: N/A rules unclear
Evidence coding agreement | ≥90% | ≥85% | <85%: evidence ladder/exemplars repair
Adjudication rate | <15% | <25% | ≥25%: excessive assessor ambiguity
Retest stability | High / context-appropriate | Pre-specified threshold | Material unexplained drift: investigate
Burden | Operationally acceptable | Pre-specified ceiling | Excessive burden: routing redesign
High-stakes verification | 100% compliant | 100% | Any release without required verification = fail
Contradiction handling | 100% hierarchy compliance | 100% | Any score released despite unresolved material contradiction = fail
Version integrity | 100% | 100% | Any untracked methodology change = fail

## 15_P0-7_Freeze_Gate
Gate | Evidence Required | Status Before Pilot | Status After Pilot | Owner | Freeze Consequence
Architecture integrity | 132 metrics / 11 dimensions / canonical IDs | PASS |  | Methodology Lead | Block freeze if broken
Assessor calibration | Independent duplicate scoring | PENDING |  | Calibration Lead | Revise anchors if weak
Inter-rater reliability | Pre-specified reliability analysis | PENDING |  | Statistician | Do not freeze if materially weak
Evidence reliability | E0–E4 agreement | PENDING |  | Evidence Lead | Repair evidence rules if weak
Validity evidence | Content/response/construct/criterion as feasible | PENDING |  | Methodology Lead | Do not claim validated if insufficient
Fairness | Subgroup/context review | PENDING |  | QA Lead | Repair if unjustified bias
Burden | Respondent + assessor burden | PENDING |  | Operations Lead | Routing redesign if excessive
Outcome governance | Denominator + role relevance + attribution | PENDING |  | Outcomes Lead | No outcome score release if unverified
N/A governance | Construct-specific N/A evidence | PENDING |  | QA Lead | No strategic N/A escape route
Version freeze | Signed build + checksum + change log | PENDING |  | Methodology Lead | Create next controlled version

## 16_Data_Dictionary
Field | Definition | Allowed / Format | Mandatory?
Case ID | Unique pilot assessment case identifier | ECRI-PILOT-#### | Yes
Institution ID | De-identified institution identifier | INST-### | Yes
Assessor ID | De-identified assessor identifier | ASM-## | Yes
Metric ID | Canonical ECRI metric ID | D01-I01 … D11-I12 | Yes
Maturity | Observed maturity level | 0–5 integer | Yes if applicable
Implementation | Implementation depth | 0–5 integer | Yes if applicable
Outcome | Outcome component where eligible | 0–100 or N/A | Only eligible metrics
Evidence | Evidence confidence | E0–E4 | Yes
N/A | Applicability decision | Applicable / N/A + gate evidence | Yes
Release Hold | Whether score cannot be released | Yes / No | Yes

## 17_132_Metric_Pilot_Registry
Metric ID | Dimension | Metric | Outcome Eligible | Measurement Type | Observation Period | Minimum Evidence | N/A Gate | Anti-Gaming | Routing Trigger
D01-I01 | Employer Demand Intelligence | Employer Demand Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I02 | Employer Demand Intelligence | Employer Intelligence Recency |  | Recency/currency/refresh interval + 0–5 maturity/implementation rubric | Current state plus dated change log over prior 24 months. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I03 | Employer Demand Intelligence | Occupational Demand Mapping |  | Defined coverage/completeness/traceability test + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I04 | Employer Demand Intelligence | Emerging Skill Detection |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I05 | Employer Demand Intelligence | Regional Labour-Market Relevance |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I06 | Employer Demand Intelligence | Sector Demand Diversity |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I07 | Employer Demand Intelligence | Employer Signal Reliability |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I08 | Employer Demand Intelligence | Demand-to-Programme Translation |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I09 | Employer Demand Intelligence | Future Demand Scenario Use |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I10 | Employer Demand Intelligence | Employer Intelligence Decision Use |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I11 | Employer Demand Intelligence | Demand Data Governance |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09.
D01-I12 | Employer Demand Intelligence | Demand Intelligence Improvement Rate |  | Rate (%) with validated denominator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D03, D09.
D02-I01 | Employability Capability Framework | Capability Taxonomy Completeness |  | Defined coverage/completeness/traceability test + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I02 | Employability Capability Framework | Capability-to-Occupation Mapping |  | Defined coverage/completeness/traceability test + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I03 | Employability Capability Framework | Capability Proficiency Definition |  | Defined coverage/completeness/traceability test + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I04 | Employability Capability Framework | Programme Capability Mapping Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I05 | Employability Capability Framework | Capability Assessment Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I06 | Employability Capability Framework | Capability Gap Detection |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D03, D06, D08.
D02-I07 | Employability Capability Framework | Capability Progression Design |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D03, D06, D08.
D02-I08 | Employability Capability Framework | Employability Credential Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I09 | Employability Capability Framework | Employer Validation of Capabilities |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I10 | Employability Capability Framework | Capability Equity Coverage |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D03, D06, D08.
D02-I11 | Employability Capability Framework | Capability Governance |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D06, D08.
D02-I12 | Employability Capability Framework | Capability Framework Refresh Rate |  | Rate (%) with validated denominator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D03, D06, D08.
D03-I01 | Industry-Aligned Curriculum | Industry-Informed Learning Outcomes |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I02 | Industry-Aligned Curriculum | Occupational Curriculum Alignment |  | Defined coverage/completeness/traceability test + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I03 | Industry-Aligned Curriculum | Curriculum Currency |  | Recency/currency/refresh interval + 0–5 maturity/implementation rubric | Current state plus dated change log over prior 24 months. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I04 | Industry-Aligned Curriculum | Professional Content Relevance |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I05 | Industry-Aligned Curriculum | Industry Validation Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I06 | Industry-Aligned Curriculum | Future Skills Integration |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I07 | Industry-Aligned Curriculum | Programme Review Effectiveness |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I08 | Industry-Aligned Curriculum | Curriculum Flexibility |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I09 | Industry-Aligned Curriculum | Professional Standards Alignment |  | Defined coverage/completeness/traceability test + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I10 | Industry-Aligned Curriculum | Work-Context Learning Coherence |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I11 | Industry-Aligned Curriculum | Programme Employability Accountability |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D03-I12 | Industry-Aligned Curriculum | Curriculum Change Responsiveness |  | Recency/currency/refresh interval + 0–5 maturity/implementation rubric | Current state plus dated change log over prior 24 months. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D02, D04.
D04-I01 | Experiential & Practice-Based Learning | Authentic Project Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I02 | Experiential & Practice-Based Learning | Work-Integrated Learning Coverage |  | Rate (%) with validated denominator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D03, D09, D08.
D04-I03 | Experiential & Practice-Based Learning | Internship/Placement Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I04 | Experiential & Practice-Based Learning | Live Industry Brief Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I05 | Experiential & Practice-Based Learning | Practice Environment Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I06 | Experiential & Practice-Based Learning | Experiential Supervision Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I07 | Experiential & Practice-Based Learning | Practice-Based Assessment |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I08 | Experiential & Practice-Based Learning | Reflection and Transfer Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I09 | Experiential & Practice-Based Learning | Project Employer Relevance |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I10 | Experiential & Practice-Based Learning | Equitable Access to Experience |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I11 | Experiential & Practice-Based Learning | Employer Participation in Learning |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D04-I12 | Experiential & Practice-Based Learning | Experiential Learning Outcome Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D03, D09, D08.
D05-I01 | Career Development Infrastructure | Career Service Capacity |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I02 | Career Development Infrastructure | Career Guidance Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I03 | Career Development Infrastructure | Career Coaching Access |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I04 | Career Development Infrastructure | Career Exploration Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I05 | Career Development Infrastructure | Job-Search Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D06, D08, D09, D10.
D05-I06 | Career Development Infrastructure | Selection/Interview Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D06, D08, D09, D10.
D05-I07 | Career Development Infrastructure | Placement Preparation |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I08 | Career Development Infrastructure | Occupational Information Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I09 | Career Development Infrastructure | Employer Exposure Access |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I10 | Career Development Infrastructure | Career Support Equity |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D06, D08, D09, D10.
D05-I11 | Career Development Infrastructure | Career Service Utilisation |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D05-I12 | Career Development Infrastructure | Transition Support Effectiveness |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D08, D09, D10.
D06-I01 | Professional & Human Capabilities | Communication Capability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I02 | Professional & Human Capabilities | Teamwork Capability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I03 | Professional & Human Capabilities | Problem-Solving Capability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I04 | Professional & Human Capabilities | Critical-Thinking Capability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I05 | Professional & Human Capabilities | Professional Judgement |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I06 | Professional & Human Capabilities | Leadership and Initiative |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I07 | Professional & Human Capabilities | Adaptability and Learning Agility |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I08 | Professional & Human Capabilities | Professional Work Behaviour |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D04, D08.
D06-I09 | Professional & Human Capabilities | Creativity and Innovation |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I10 | Professional & Human Capabilities | Ethical Judgement |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I11 | Professional & Human Capabilities | Self-Management and Resilience |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D04, D08.
D06-I12 | Professional & Human Capabilities | Interpersonal Effectiveness |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D04, D08.
D07-I01 | Digital & AI-Era Work Readiness | Digital Work Literacy |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I02 | Digital & AI-Era Work Readiness | AI Work Literacy |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I03 | Digital & AI-Era Work Readiness | AI Productivity Capability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I04 | Digital & AI-Era Work Readiness | AI Verification and Judgement |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I05 | Digital & AI-Era Work Readiness | Digital Collaboration |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D03, D08.
D07-I06 | Digital & AI-Era Work Readiness | Workplace Data Literacy |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I07 | Digital & AI-Era Work Readiness | Digital Problem Solving |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D03, D08.
D07-I08 | Digital & AI-Era Work Readiness | Cyber/Privacy Work Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I09 | Digital & AI-Era Work Readiness | Tool Adaptability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D02, D03, D08.
D07-I10 | Digital & AI-Era Work Readiness | Human-AI Collaboration |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D03, D08.
D07-I11 | Digital & AI-Era Work Readiness | AI-Era Role Awareness |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D03, D08.
D07-I12 | Digital & AI-Era Work Readiness | Digital/AI Capability Validation |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D02, D03, D08.
D08-I01 | Portfolio & Capability Signalling | Portfolio Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I02 | Portfolio & Capability Signalling | Work-Sample Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I03 | Portfolio & Capability Signalling | Project Evidence Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I04 | Portfolio & Capability Signalling | Capability Narrative Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I05 | Portfolio & Capability Signalling | CV/Resume Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D06, D07, D10.
D08-I06 | Portfolio & Capability Signalling | Interview Evidence Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D06, D07, D10.
D08-I07 | Portfolio & Capability Signalling | Professional Digital Presence |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I08 | Portfolio & Capability Signalling | Credential Signal Strength |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I09 | Portfolio & Capability Signalling | Employer-Facing Signal Quality |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I10 | Portfolio & Capability Signalling | Student Evidence Ownership |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I11 | Portfolio & Capability Signalling | Evidence Authenticity |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D08-I12 | Portfolio & Capability Signalling | Capability Signal Effectiveness |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D06, D07, D10.
D09-I01 | Employer Engagement & Recruitment Ecosystem | Employer Network Breadth |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I02 | Employer Engagement & Recruitment Ecosystem | Employer Relationship Depth |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I03 | Employer Engagement & Recruitment Ecosystem | Advisory Engagement Effectiveness |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I04 | Employer Engagement & Recruitment Ecosystem | Industry Co-Creation |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I05 | Employer Engagement & Recruitment Ecosystem | Recruiter Engagement |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I06 | Employer Engagement & Recruitment Ecosystem | Recruitment Ecosystem Strength |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I07 | Employer Engagement & Recruitment Ecosystem | Internship Partnership Strength |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I08 | Employer Engagement & Recruitment Ecosystem | Mentoring/Networking Access |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I09 | Employer Engagement & Recruitment Ecosystem | Employer Confidence |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I10 | Employer Engagement & Recruitment Ecosystem | Repeat Employer Engagement |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I11 | Employer Engagement & Recruitment Ecosystem | Employer Diversity |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D09-I12 | Employer Engagement & Recruitment Ecosystem | Employer Ecosystem Governance |  | Structured quality/effectiveness rubric using multiple evidence sources + 0–5 implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D01, D04, D10.
D10-I01 | Employment Outcome Quality | Employment Outcome Coverage |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I02 | Employment Outcome Quality | Relevant Employment Rate |  | Rate (%) with validated denominator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I03 | Employment Outcome Quality | Role Quality |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I04 | Employment Outcome Quality | Compensation Quality |  | Median/percentile compensation for relevant outcomes + 0–5 rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I05 | Employment Outcome Quality | Employer Quality |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I06 | Employment Outcome Quality | Sector/Role Distribution |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I07 | Employment Outcome Quality | Time-to-Employment |  | Median days/months to first relevant outcome + distribution + 0–5 rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I08 | Employment Outcome Quality | Outcome Transparency |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I09 | Employment Outcome Quality | Underemployment/Mismatch Rate |  | Rate (%) with validated denominator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I10 | Employment Outcome Quality | Further Study and Entrepreneurship Outcomes |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I11 | Employment Outcome Quality | Outcome Durability |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D10-I12 | Employment Outcome Quality | Outcome Equity |  | Outcome indicator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D05, D08, D09, D11.
D11-I01 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Career Adaptability |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D10, D05, D01.
D11-I02 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Career Self-Management |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D10, D05, D01.
D11-I03 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Lifelong Learning Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D10, D05, D01.
D11-I04 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Occupational Mobility |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.
D11-I05 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Transition Readiness |  | Direct learner capability evidence using rubric/work sample/observation + 0–5 institutional implementation rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D10, D05, D01.
D11-I06 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Alumni Career Intelligence |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.
D11-I07 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Graduate Trajectory Coverage |  | Coverage/access/utilisation rate (%) + 0–5 maturity/implementation rubric | Most recent completed academic year; prior 2 years for trend where available. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.
D11-I08 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Outcome Feedback Loop |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.
D11-I09 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Employability Intelligence Use |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.
D11-I10 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Post-Graduation Support |  | Process/capability demonstration + evidence-coded 0–5 rubric | Current operating cycle plus most recent completed academic year; retain prior-year evidence where trend/learning is claimed. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.
D11-I11 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Institutional Learning Rate |  | Rate (%) with validated denominator + 0–5 maturity/implementation rubric | Most recent completed graduating cohort + prior 2 cohorts where available; report cohort, denominator and censoring rule. |  | N/A only if the outcome is genuinely not observable/applicable for the declared institutional context or cohort; approval and reason required. Missing outcome data is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; Level 4–5 claim or material learner/outcome assertion; inspect dependencies D10, D05, D01.
D11-I12 | Career Adaptability, Lifelong Readiness & Employability Intelligence | Continuous Employability Improvement |  | Recency/currency/refresh interval + 0–5 maturity/implementation rubric | Current state plus dated change log over prior 24 months. |  | N/A only when the construct is genuinely inapplicable to the declared context/population; assessor approval and explicit scope rationale required. Missing/weak evidence is not N/A. |  | R2 Partly; R4 Unclear; R6 Contradictory; weak/absent E2+ evidence; high-stakes claim; inspect dependencies D10, D05, D01.

## 18_Change_Log
Change ID | Date | Version | Change | Reason | Approved By | Impact | Status
P7-001 | 2026-09-14 | v1 | Created live multi-assessor pilot protocol | Round 4/5 synthetic calibration requires empirical pilot | Pending | P0-7 live validation | Open